BIDINTELL

6-MONTH GROWTH PLAYBOOK

February 18 – August 15, 2025

MISSION

Grow from 0 to 500 active users spending 1-2 hours/day
on the highest-impact activities.

| Phase 1 Weeks 1-4 Beta Launch | Phase 2 Weeks 5-8 PMF Validation | Phase 3 Weeks 9-14 Content Engine | Phase 4 Weeks 15-26 Scale to 500 |
| --- | --- | --- | --- |

## 🎯 Core Principles for This Plan

• 1-2 hours/day maximum — every activity is high-leverage

• Personal outreach beats mass marketing at your stage — always

• Your 10 years in construction is your unfair advantage — lead with it everywhere

• Data from your platform becomes content — more users = more insights = more content

• Never let a week go by without a LinkedIn post, a demo call, or a user check-in

## 💡 Viral & Creative Distribution Ideas

These go beyond standard tactics and can accelerate growth significantly:

1. The Bid Win Rate Calculator (Free Lead Magnet)

Build a simple free web tool: 'What's your true bid win rate — and what is chasing bad bids costing you?' Requires email to see results. High shareability among subcontractors. Estimated 300-500 leads per month if promoted correctly.

2. The Annual GC Responsiveness Report

Aggregate your growing dataset into an annual (then quarterly) report ranking GC types by responsiveness, ghosting rates, and subcontractor satisfaction. This becomes a PR asset, a press magnet, and establishes BidIntell as the industry's data authority. Think: 'Glassdoor for GCs.'

3. Shareable BidIndex Score Cards

Let users share their monthly BidIndex summary as a LinkedIn post — similar to Spotify Wrapped. '87% of bids I analyzed this month were PASS recommendations. I saved 40+ hours of estimating time.' Every share is free advertising.

4. The 'Bid Smarter Challenge'

30-day LinkedIn challenge: document every bid you analyze for 30 days using BidIntell. Users post their score + outcome. Creates FOMO, community, and user-generated content simultaneously.

5. Trade Association Partnership Play

Contact your local NECA (electrical), MCAA (mechanical), or SMPS chapter and offer BidIntell as a member benefit at a group discount. One deal = instant access to 50-200 subcontractors who trust the association's recommendation.

6. Construction Estimating Facebook Groups

Groups like 'Construction Estimators Network' (50K+ members) are untapped. Add genuine value for 2-4 weeks before any mention of BidIntell. Then share a genuine insight from your data. These groups drive high-quality, pre-qualified leads.

PHASE 1: BETA LAUNCH & VALIDATION Feb 18 – Mar 18, 2025 ¦ Goal: 10 active beta users, 50+ bids analyzed

| WEEK 1 Feb 18–21 — Beta Recruitment Blitz |  |
| --- | --- |
| DAILY TASKS | Morning (30 min): Review any beta signups/messages from previous day Send 5-10 personalized DMs or texts to your FSI network contacts Evening (30 min): Engage with 3-5 LinkedIn posts in construction community |
| WEEKLY GOALS | Sign up 3-5 beta users from your direct FSI network Add demo video link to website homepage (Loom screen recording, 3-5 min) Create simple CRM tracking sheet (Name, Company, Trade, Status, Notes) Send personal 'I built this, want to try it?' texts to your top 20 contacts |
| CONTENT & OUTREACH | LinkedIn Post #1: 'After 10 years in construction, I got tired of guessing which bids were worth our time...' (origin story post) Direct text/call FSI subcontractor contacts — personal > everything LinkedIn Post #2: Show a real BidIndex score screenshot (blur the GC name) with commentary |

| WEEK 2 Feb 24–28 — Onboarding & First Feedback |  |
| --- | --- |
| DAILY TASKS | Check in with every beta user daily (text/call, not just email) Watch Loom recordings if you add session recording (FullStory free tier) Fix any bug reported within 24 hours — speed builds massive trust |
| WEEKLY GOALS | Get first 5 beta users fully onboarded and analyzing real bids Conduct 3 live demo calls via Zoom/phone with potential users Collect first NPS-style feedback: 'Does the score match your gut?' (1-10) Identify your top 2-3 most engaged users — these become your champions |
| CONTENT & OUTREACH | LinkedIn Post #3: 'I built a tool that scores construction bids 0-100. Here's the logic behind the score...' (educational) Reach out to 2-3 trade associations (electrical, plumbing, HVAC) about beta program Post in Contractor Talk forum: 'Testing AI bid analysis tool, need beta testers' |

| WEEK 3 Mar 3–7 — Proof of Concept Documentation |  |
| --- | --- |
| DAILY TASKS | Run a bid analysis yourself using an FSI bid — dog food your own product Send Monday check-in message to all beta users Screenshot any positive feedback for future testimonials |
| WEEKLY GOALS | Reach 10 active beta users Have 25+ bids analyzed across your user base Get 2-3 written or recorded testimonials ('Before/After' format) Identify the ONE feature users love most and the ONE thing missing |
| CONTENT & OUTREACH | LinkedIn Post #4: 'We've analyzed 25 bids so far. Here's what the data shows about which GCs are worth bidding for...' Email your wider FSI network: 'I built something — want a free look?' LinkedIn Post #5: Repost a beta user win story (with permission) |

| WEEK 4 Mar 10–14 — Iterate & Expand |  |
| --- | --- |
| DAILY TASKS | Review feedback patterns — what's the #1 request? Spend 30 min on one improvement based on beta feedback Schedule demo calls with warm leads in pipeline |
| WEEKLY GOALS | Fix top 3 friction points from beta feedback Validate pricing: ask each user 'Would you pay $49/month? $99/month?' Start building your waitlist email list (Mailchimp free tier) Create a referral offer: 'Refer a sub, both get an extra month free' |
| CONTENT & OUTREACH | LinkedIn Post #6: 'Biggest lessons from our first month of beta testing...' (transparency builds trust) Reach out to 5 estimators you know personally with a direct ask LinkedIn Post #7: 'The GC ghosting problem — data from our first 50 analyses' |

PHASE 2: PRODUCT-MARKET FIT Mar 17 – Apr 11, 2025 ¦ Goal: 25-50 users, validate 'would pay $99/mo'

| WEEK 5 Mar 17–21 — Launch Public Beta |  |
| --- | --- |
| DAILY TASKS | Monitor signups and respond to every application within 2 hours Post to LinkedIn daily — momentum builds momentum Message 5 new cold contacts per day on LinkedIn |
| WEEKLY GOALS | Open beta to wider audience — announce on LinkedIn, Contractor Talk, Reddit r/Construction Create a proper 'Apply for Beta' landing page flow Target: 10 new signups from outside your direct network Set up a Calendly link for 30-min demo calls |
| CONTENT & OUTREACH | LinkedIn Post #8: 'BidIntell is now accepting beta applications — here's how to get in' (with link) Reddit r/Construction post: 'Built an AI bid scoring tool for subs, looking for beta testers' LinkedIn Post #9: Educational — 'The hidden cost of chasing every bid' (hook with data) |

| WEEK 6 Mar 24–28 — Demo & Convert |  |
| --- | --- |
| DAILY TASKS | Run at least 2 demo calls per day (use real bids from their trade/region) Follow up with every demo within 24 hours Track conversion rate: demo to active user |
| WEEKLY GOALS | 30 total demos completed Convert 50% of demos to active beta users Build your first case study: one user, real bid, real outcome Survey all users: NPS score + 'what would make this worth $99/month?' |
| CONTENT & OUTREACH | LinkedIn Post #10: 'I did 20 demos this week. Here's the #1 question I keep getting...' Create a short Loom case study: analyze a real bid live on screen (educational content + product demo) LinkedIn Post #11: Share the case study publicly (blur company names) |

| WEEK 7 Mar 31–Apr 4 — Viral Mechanics |  |
| --- | --- |
| DAILY TASKS | Identify your 3 most active users — give them white-glove treatment Look for any organic referrals — who referred who? Engage with every comment on your LinkedIn posts within 1 hour |
| WEEKLY GOALS | Launch referral program: 'Refer a sub, get 2 months free' Target: 5 organic referrals from existing beta users Reach 40 total active users Create a 'BidIndex Score' shareable card users can post on LinkedIn (viral mechanic) |
| CONTENT & OUTREACH | LinkedIn Post #12: 'Our users are now scoring bids before estimating. The results are surprising...' VIRAL IDEA: Post 'What's your bid win rate? Most subs don't know. Here's how to calculate it.' — drives engagement and demonstrates the problem BidIntell solves Contractor Talk / Reddit: share the win rate calculator concept |

| WEEK 8 Apr 7–11 — PMF Checkpoint |  |
| --- | --- |
| DAILY TASKS | Review ALL feedback from past 8 weeks — look for patterns Prepare PMF survey for all users Plan next phase based on data |
| WEEKLY GOALS | Send formal PMF survey: 'How disappointed would you be if BidIntell disappeared?' (target: 40%+ 'very disappointed') Validate: 7/10 users say 'I would pay $99/month' 50+ bids analyzed total — document extraction accuracy rates Decide: ready to scale, or need more iteration? |
| CONTENT & OUTREACH | LinkedIn Post #13: '8-week beta update — what we learned from analyzing 100+ bids' (milestone post, drives credibility) Compile 3 written testimonials ready for website LinkedIn Post #14: Announce Phase 1.5 — converting to paid (creates urgency for remaining free spots) |

PHASE 3: CONTENT ENGINE & ORGANIC GROWTH Apr 14 – May 23, 2025 ¦ Goal: 75-150 users, content flywheel running

| WEEK 9 Apr 14–18 — Convert Beta to Paid |  |
| --- | --- |
| DAILY TASKS | Personal call/text to every beta user about converting to paid Post LinkedIn content — shift from 'beta' framing to 'early adopter' framing Monitor churn signals closely |
| WEEKLY GOALS | Convert 50%+ of beta users to $49/month Starter plan First paying customers — celebrate and share this milestone on LinkedIn Add testimonials and social proof to website homepage Set up proper onboarding email sequence (3-email drip) |
| CONTENT & OUTREACH | LinkedIn Post #15: 'We just got our first paying customers. Here's what made them say yes.' Create 'BidIntell vs. gut instinct' comparison post — use anonymized data from beta YouTube/Loom: Record your first official product walkthrough video (10 min) |

| WEEK 10 Apr 21–25 — LinkedIn Authority Build |  |
| --- | --- |
| DAILY TASKS | Post on LinkedIn daily — alternate between educational, behind-the-scenes, data insights Spend 20 min commenting on other construction industry posts (visibility) DM 5 new construction estimators/subcontractors per day |
| WEEKLY GOALS | Reach 500 LinkedIn followers on personal profile Create BidIntell company LinkedIn page — post 3x/week Identify 5 construction podcast hosts to pitch as a guest Write first blog post for website: 'The Data Behind Construction Bid Win Rates' |
| CONTENT & OUTREACH | LinkedIn Hook Post: 'The average subcontractor bids 4x more than they should. Here's the math.' (high shareability) LinkedIn Post: '5 red flags in a bid invitation that predict you'll get ghosted' (practical, drives saves) LinkedIn Post: 'I analyzed 100 bid invitations with AI. Here's what surprised me.' |

| WEEK 11 Apr 28–May 2 — Community & Partnerships |  |
| --- | --- |
| DAILY TASKS | Engage in Contractor Talk and r/Construction daily Follow up on any podcast pitch responses Continue DM outreach on LinkedIn |
| WEEKLY GOALS | Get into 2-3 construction Facebook groups and add genuine value before any promotion Reach out to 3 construction-focused YouTube channels about a collaboration Contact your local AGC (Associated General Contractors) chapter about partner program Target: 100 total active users |
| CONTENT & OUTREACH | VIRAL IDEA: Create a free 'Bid Win Rate Calculator' as a lead magnet — simple web tool that shows subs their true win rate and what it costs them in estimating time. Capture email at the end. LinkedIn Post: Share the free calculator — high share potential Reddit: Share the calculator as a genuinely useful free resource |

| WEEK 12 May 5–9 — Referral Engine |  |
| --- | --- |
| DAILY TASKS | Check referral program metrics daily Text your top 5 users: 'Who do you know that would love this?' Follow up on all open demo pipeline |
| WEEKLY GOALS | 25% of new signups from referrals Launch 'Refer a Friend' email campaign to all current users Record and publish first proper case study video (YouTube + LinkedIn) Apply to be a speaker at one construction industry event (AGC, SMPS, etc.) |
| CONTENT & OUTREACH | LinkedIn: Publish the case study — '$47,000 project they almost passed on — here's what our AI said' LinkedIn Post: 'We hit 100 bids analyzed. Here's the pattern no one talks about.' Email newsletter #1 to your user list: Monthly insights from the data |

| WEEK 13 May 12–16 — SEO & Inbound |  |
| --- | --- |
| DAILY TASKS | 20 minutes of LinkedIn engagement (comments, not just posts) Track which content gets the most saves/shares — double down Continue demo calls for warm leads |
| WEEKLY GOALS | Publish 2 SEO blog posts targeting: 'construction bid analysis software', 'subcontractor bid scoring' Submit BidIntell to SaaS directories: G2, Capterra, Product Hunt (soft launch) Get first press mention: pitch to Construction Dive, ENR, or a regional construction publication Target: 150 total users |
| CONTENT & OUTREACH | Product Hunt launch prep — draft listing, gather upvotes from your beta user network LinkedIn: 'The question every subcontractor should ask before spending time on an estimate' (lead gen hook) LinkedIn: Data post using aggregated (anonymous) insights from your growing dataset |

| WEEK 14 May 19–23 — First Podcast & Press |  |
| --- | --- |
| DAILY TASKS | Prepare podcast talking points: your construction background, the insight, the solution, the data Continue outreach cadence Review pricing — is anyone asking for a higher tier? |
| WEEKLY GOALS | Record first podcast appearance (even a local or small show is great for credibility) Get one media mention or newsletter feature Launch Product Hunt listing Survey users again — track PMF score improvement |
| CONTENT & OUTREACH | LinkedIn: Announce the podcast episode when it drops LinkedIn: 'What I learned building a construction tech startup after 10 years in the field' (founder story, high engagement) Email newsletter #2: Share the podcast, share data insights, highlight a user win |

PHASE 4: SCALE TO 500 USERS May 26 – Aug 1, 2025 ¦ Goal: 300-500 users, $15K-25K MRR, partnership conversations

| WEEK 15 May 26–30 — Upgrade Tier Launch |  |
| --- | --- |
| DAILY TASKS | Monitor upgrade conversion rates Personal outreach to power users about Pro tier benefits Double down on highest-converting content types |
| WEEKLY GOALS | Launch Professional tier ($99/month) with enhanced features Target 20% of users on Pro tier Begin email forwarding feature development (Phase 2 tech) Create upgrade email campaign for existing Starter users |
| CONTENT & OUTREACH | LinkedIn: Announce Pro tier — frame around value ('save 5 hours/week of estimating time') LinkedIn: 'The ROI of knowing which bids to skip — real numbers from our users' Case study blog post: document a specific user win with permission |

| WEEK 16 Jun 2–6 — LinkedIn Ads Test |  |
| --- | --- |
| DAILY TASKS | Review ad performance daily — cut losers fast Continue organic content (ads amplify organic, don't replace it) Check in with churned users — what made them leave? |
| WEEKLY GOALS | Launch LinkedIn ad test: $500/month budget targeting construction estimators A/B test 2 ad creatives: data-driven vs. pain-point framing Track Cost Per Lead and Cost Per Acquisition — target CAC under $300 200 total users milestone |
| CONTENT & OUTREACH | LinkedIn: '3 bids our AI flagged as high-risk — and why the subs who skipped them made the right call' LinkedIn: 'The one number every subcontractor needs to track (and almost none do)' Email newsletter #3: Monthly data roundup + product update |

| WEEK 17 Jun 9–13 — Strategic Outreach |  |
| --- | --- |
| DAILY TASKS | Work the partnership list — research contacts at target companies Continue content engine Monitor trial-to-paid conversion rates |
| WEEKLY GOALS | Identify and warm up 3 potential integration partners (Togal.AI, PlanHub, ConstructConnect) Reach out to Togal.AI contact — share mutual user base angle Submit to 3 more SaaS directories Achieve 60% weekly retention rate |
| CONTENT & OUTREACH | VIRAL IDEA: Launch 'GC Responsiveness Report' — aggregate (anonymous) data on which GC types respond vs. ghost subs. This becomes a PR asset and lead magnet. LinkedIn: Tease the GC Responsiveness Report — 'dropping next week' Pitch the report to Construction Dive as an exclusive data story |

| WEEK 18 Jun 16–20 — GC Report PR Launch |  |
| --- | --- |
| DAILY TASKS | Respond to every piece of press coverage immediately Monitor inbound leads from report Share report in every relevant construction community |
| WEEKLY GOALS | Publish the GC Responsiveness Report publicly Pitch to 5 construction media outlets 300 total users milestone At least 1 press pickup |
| CONTENT & OUTREACH | LinkedIn: Publish the full report with key findings (long-form, high share potential) LinkedIn: Thread breaking down the top 5 findings Email newsletter #4: Send the report to your entire list |

| WEEK 19–22 Jun 23–Jul 18 — Scale & Optimize |  |
| --- | --- |
| DAILY TASKS | Focus: whichever acquisition channel is working — double down Weekly: review retention, churn, and upgrade data Monthly: run another PMF survey |
| WEEKLY GOALS | 400 total users 30% referral rate target First partnership pilot conversation (Togal.AI or similar) Apply to construction tech accelerators/pitch competitions for visibility |
| CONTENT & OUTREACH | Monthly webinar: 'How to Analyze a Construction Bid Before You Estimate It' (free, lead gen) Continue LinkedIn 3x/week — shift to more data-driven content as dataset grows Guest post on construction industry blogs Email newsletter monthly — become the 'construction bidding data' source |

| WEEK 23–26 Jul 21–Aug 15 — 500 User Milestone & Phase 3 Prep |  |
| --- | --- |
| DAILY TASKS | Document everything for Phase 3 intelligence layer build Analyze your best acquisition channels — prepare to scale what works Begin GC database development planning |
| WEEKLY GOALS | 500 total users — celebrate publicly on LinkedIn (social proof milestone) Begin Phase 3 development: GC intelligence database Initiate formal partnership conversation with at least one platform Raise prices for new users — test $149/month Starter |
| CONTENT & OUTREACH | LinkedIn: '500 subcontractors. 5,000+ bids analyzed. Here's what the data shows.' (milestone post — high viral potential) Press release: 500 users milestone, share with construction media Podcast: pitch to larger construction shows now that you have significant social proof |

## 📊 Monthly KPI Tracker

Track these numbers every week. What gets measured gets managed.

| Metric | Month 1 Target | Month 3 Target | Month 6 Target | Actual |
| --- | --- | --- | --- | --- |
| Active Users | 10 | 100 | 500 |  |
| Bids Analyzed | 50+ | 500+ | 3,000+ |  |
| Weekly Retention | 50%+ | 60%+ | 70%+ |  |
| Would Pay $99/mo | 50%+ | 65%+ | 75%+ |  |
| Referral Rate | — | 20%+ | 30%+ |  |
| LinkedIn Followers | 200 | 1,000 | 3,000+ |  |
| MRR | $0 (beta) | $3K-8K | $20K-40K |  |
| Demo-to-User Rate | — | 40%+ | 50%+ |  |

## 📋 LinkedIn Content Calendar — Themes by Week

Rotate between these 5 content pillars to keep your feed varied and valuable:

🏗️  EDUCATION (2x/month): Construction bidding tips, estimating best practices, industry data. 'What the data shows...' framing.

💡  INSIGHT (1x/week): An unexpected finding from your growing dataset. Sub count hit 200? Now you have real data to share.

🎯  PRODUCT (1x/week): Feature updates, use cases, user wins. Make it about THEIR outcomes, not your product.

👷  FOUNDER STORY (1x/month): Vulnerability and honesty about building in public. Your 10 years + building BidIntell = compelling narrative.

📣  SOCIAL PROOF (1x/month): Testimonials, case studies, milestone announcements. Numbers + real stories.

## ✅ Never Miss These Non-Negotiables

No matter how busy the week gets, protect these activities:

DAILY: Check in with at least 2 active users (text/Slack/email). Respond to every LinkedIn comment. Send 5 DMs to new prospects.

WEEKLY: Post 3x on LinkedIn. Run at least 2 demo calls. Review your KPI numbers. Fix 1 bug or improve 1 feature based on feedback.

MONTHLY: Send the newsletter. Survey your users (NPS + feature feedback). Publish 1 case study or data insight piece. Set 4 goals for next month.

Remember: The subcontractors you're trying to reach are exactly who you used to be.

Lead with that. Everything else follows.